## Test Cases
TC_ID | Test Case Description | Precondition | Steps | Expected Result
CTC001 | Verify Addition | Calculator is open | Enter 2 + 3 = | Output should be 5
CTC002 | Verify Subtraction | Calculator is open | Enter 7 - 2 = | Output should be 5
CTC003 | Verify Multiplication | Calculator is open | Enter 4 × 5 = | Output should be 20
CTC004 | Verify Division | Calculator is open | Enter 10 ÷ 2 = | Output should be 5
CTC005 | Division by Zero Handling | Calculator is open | Enter 5 ÷ 0 = | Error message, no crash
CTC006 | Large Number Multiplication | Calculator is open | Enter 99999999 × 99999999 | Should handle gracefully
CTC007 | Verify Clear Button | Calculator is open | Perform a calculation → Press C/AC | Screen should reset to 0
CTC008 | Verify Decimal Calculations | Calculator is open | Enter 5.5 + 2.2 = | Output should be 7.7

## Execution Results
TC_ID | Expected Result | Actual Result | Status
CTC001 | Output 5 | Output 5 | Pass
CTC002 | Output 5 | Output 5 | Pass
CTC003 | Output 20 | Output 20 | Pass
CTC004 | Output 5 | Output 5 | Pass
CTC005 | Show error for ÷0 | ‘Cannot divide by zero’ shown | Pass
CTC006 | Should handle large input | Calculator froze | Fail
CTC007 | Screen resets to 0 | Screen cleared successfully | Pass
CTC008 | Output 7.7 | Output 7.7 | Pass

## Bug Report
Bug_ID | Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Status
B001 | Calculator freezes on large input | Enter 99999999 × 99999999 | Should calculate or show error | Calculator froze | Medium | Open